## Feuil1
Status
[9 empty] | IFR | Issue for review/comments
Equipement | TAG | Drawing number | Rev | Title | Author | Status | Date | Manufacturing lot | INF | Issue for information
Sterilisator | ST-20 |  | 2 | 25-1539 – Manufacturing - Specifications | BP | IFC | 2026-06-09 | Lot 3 - sterilisator | IFA | Issue for Approval
Sterilisator | ST-20 | 25-1539-ST-002-050 | 1 | Sterilisator Assembly | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | IFI | Issue for inquiry
Sterilisator | ST-20 | 25-1539-ST-002-030 | 1 | Pressure gauge assembly | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | IFP | Issue for purchase
Sterilisator | ST-20 | 25-1539-ST-002-001 | 1 | Sterilisator | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | IFE | Issue for Design execution
Sterilisator | ST-20 | 25-1539-ST-002-002 | 1 | Front door | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-003 | 1 | Corner door | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-004 | 1 | Exit door | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-005 | 1 | Crown entrance and exit | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-006 | 1 | Door seal | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | IFC | Issue for construction
Sterilisator | ST-20 | 25-1539-ST-002-007 | 1 | Entrance and exit door handle | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | EXE | Issue for execution
Sterilisator | ST-20 | 25-1539-ST-002-008 | 1 | Door handle washer for entrance and exit | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | ASB | As built
Sterilisator | ST-20 | 25-1539-ST-002-010 | 1 | Exit door handle | JM | IFC | 2026-06-29 | Lot 3 - sterilisator | CLD | Cancelled
Sterilisator | ST-20 | 25-1539-ST-002-011 | 1 | Foot chassis sterilisator | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-013 | 1 | Underfloor piping | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-017 | 1 | Union fitting | JM | IFC | 2026-06-29 | Lot 3 - sterilisator
Sterilisator | ST-20 | 25-1539-ST-002-019 | 1 | Sterilisator chassis | JM | IFC | 2026-06-29 | Lot 3 - sterilisator